## 1-Summary
Appendix G - Cost Proposal
Vendor: | Speridian Technologies
City of Berkeley, California
Cost Categories | Total Cost | Explanation/Notes (if necessary)
Project Costs
Implementation Fees (Sheet 2) | 2268800
5 Year Annual Cost Post Go Live (Sheet 3) | 1657368.4463
Other Fees (Sheet 4)
Total Implementation + 5 Year Costs | 3926168.4463

## 2-Implementation Fees
2 - Implementation Fees |  |  | 2 - Implementation Fees
Vendor: | Speridian Technologies |  | Vendor:
IMPLEMENTATION DELIVERABLE / TASK | PAYMENT AMOUNT | COMMENTS | IMPLEMENTATION DELIVERABLE / TASK | PAYMENT AMOUNT | COMMENTS
PROJECT MANAGEMENT | 266584 |  | PROJECT MANAGEMENT | $
REQUIREMENTS & DESIGN (Architect Solution) | 136128
DEVELOPMENT (Build, Configure, Integrate, Test) | 930208
INTEGRATION | 272256
DATA MIGRATION | 204192 |  | DATA MIGRATION
TRAINING | 22688 |  | TRAINING
SIT | 136128
UAT | 181504
DEPLOYMENT (CUTOVER SUPPORT) | 28360
POST GO LIVE HEALTH CHECK | 90752 |  | POST GO LIVE HEALTH CHECK
| 2268800 |  |  | $ -
OPTIONAL ITEM |  |  | OPTIONAL ITEM
DELIVERABLE / TASK # | PAYMENT AMOUNT | COMMENTS | DELIVERABLE / TASK # | PAYMENT AMOUNT | COMMENTS
| $ | Projected Dates (from Plan) |  | $
SOW Signature (10%) | 226880 | 2025-06-27
Initiation: Project Kickoff (10%) | 226880 | 2025-07-25
Discovery: Completion of Project Plan / Signoff (10%) | 226880 | 2026-02-23
Discovery: End of Discovery (BRD, SDD, TDD) / Signoff (10%) | 226880 | 2026-03-23
Build: Solution Checkpoint 1 (Demo) Signoff (5%) | 113440 | 2026-04-20
Build: Solution Checkpoint 2 (Demo) Signoff (5%) | 113440 | 2026-05-18
Build: Solution Checkpoint 3 (Demo) Signoff (5%) | 113440 | 2026-06-15
Build: Solution Checkpoint 4 (Demo) Signoff (5%) | 113440 | 2026-07-13
Build: Solution Checkpoint 5 (Demo) Signoff (5%) | 113440 | 2026-08-10
Build: Solution Checkpoint 6 (Demo) Signoff (5%) | 113440 | 2025-06-16
Build: Development Complete - Signoff (5%) | 113440 | 2025-07-14
Validate: Completion of SIT (5%) | 113440 | 2024-01-26
Validate: Completion of UAT (5%) | 226880 | 2025-07-14
Roll-Out: Go-Live (5%) | 226880 | 2024-01-26
| 2268800 |  |  | $ -

## 3-Annual Cost Post Go Live
3 - Annual Cost Post Go Live
Vendor: | Speridian Technologies
ITEM NAME | YEAR 1 COST | YEAR 2 COST | YEAR 3 COST | YEAR 4 COST | YEAR 5 COST | COMMENTS
Clariti Enterprise - Community Developement | 299941.92 | 314939.016 | 330685.9668 | 347220.2651 | 364581.2784 | 1. Any purchase order generated on this quote indicates acceptance of all terms and conditions on the Clariti Software Agreement.
- Platform User License - Enhanced (164) | [5 empty] | 2. Warranty is provided concurrent to licensing subscription, provided that all Clariti managed packages are kept within 1 year up to date.
- Admin User License - Enhanced (4) | [5 empty] | 3. All User Licenses enable the users to use up to 30 custom objects beyond those in Clariti's managed packages, provided they are within the scope of, and for use exclusively with, the Clariti permitting and licensing application.
- Customer Community Logins (6,000/month) | [5 empty] | 4. All Community Licenses enable users assigned this license to access up to 10 custom objects beyond those included in Clariti's managed packages.
- Clariti Salesforce Shield (1) | [5 empty] | 5. Starting in Year 2, Clariti reserves the right to increase prices up to the greater of 5% or the annual change in the Consumer Price Index statistics published by the United States Bureau of Labor.
- Clariti Sandbox, Full (1) | [5 empty] | 6. Clariti Admin User License included at no cost.
- Clariti Knowledge (1)
- Clariti ESRI ArcGIS Integration (1)
- Clariti Bluebeam Integration (1)
- Clariti Payments (1)
Total | 299941.92 | 314939.016 | 330685.9668 | 347220.2651 | 364581.2784
OPTIONAL ITEMS
ITEM NAME | YEAR 1 COST | YEAR 2 COST | YEAR 3 COST | YEAR 4 COST | YEAR 5 COST | COMMENTS
Clariti Guide | 25000 | 26250 | 27562.5 | 28940.625 | 30387.6562
Clariti Guide Implementation (one time cost) | 22500
Speridian Managed Services Support |  | 25000 | 125000 | 131250 | 137812.5 | Speridian Managed Services would begin aftet Hypercare warranty support period Post go-live.
Total | 47500 | 51250 | 152562.5 | 160190.625 | 168200.1562
2883680.936

## 4-Other
4 - Other Fees
Vendor: | Speridian Technologies
Description | Cost | Scope Option #2 Cost
Total | 0 | 0