## Project Schedule Ph 1 Bldg Perm
WBS No. |  | Month 0 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5
Task/Phase
Berkeley, California
1 | Information Gathering Phase
1.1 | Provide Setup Checklist
1.2 | Provide As-Is and To-Be & Process Documents
1.3 | Provide List & Examples of Forms, Notices, Letters, Etc.
1.4 | Provide List of Users & Security Rights
1.5 | Provide Legacy Data Sources
1.5.1 | Provide Copies of Accela Legacy Databases
1.5.2 | Provide Copies of Excel Spreadsheets
1.5.3 | Provide Copies of SolarAPP+ Databases
1.5.4 | Provide Copies of SAIRA Databases
1.5.5 | Provide Copies of FUND$ Databases
2 | Planning Phase
2.1 | Develop Comprehensive Project Plan
2.2 | Develop Technical Infrastructure Design & Implementation Plan
Building Permitting
3 | Building Permitting System Setup and Configuration Phase
3.1 | Conduct Building Permitting Weekly Walkthroughs
3.2 | Practice with New Building Permitting Functionality, Provide Feedback
3.3 | Create System Design Document
3.4 | Configure Building Permitting Installation, Forms, Notices, Letters, Reports
3.5 | Configure Building Permitting User Accounts and Rights
System Integration
3.6 | Develop Integration Document
3.7 | Develop and Test Integration Programs
Building Permitting Data Conversion
3.8 | Develop Building Permitting Data Conversion Document
3.9 | Develop and Test Building Permitting Conversion Scripts
Building Permitting Data Conversion Acceptance
4 | Building Permitting System Readiness Phase
4.1 | Create Building Permitting User Acceptance Test Scripts and Plan
4.2 | Perform Building Permitting User Acceptance Testing
4.3 | Provide Feedback on Building Permitting Issues, Changes
4.4 | Update Citizenserve Building Permitting Configuration
4.5 | Conduct Pre-production Security Testing
5 | Building Permitting Training Phase
5.1 | Create Building Permitting Training Documents for City Users
5.2 | Provide Building Permitting Training for City Users
5.3 | Create Building Permitting Training Documents for City System Administrators
5.4 | Provide Building Permitting Training for City System Administrators
5.5 | Create Building Permitting System Documentation/Manuals
6 | Building Permitting Implementation Phase
6.1 | Develop Building Permitting Cutover Plan
6.2 | Configure Building Permitting Production Instance
6.3 | Configure Integration Points in Production
6.4 | Convert Building Permitting Legacy Data to Production
7 | Building Permitting Go-Live Phase
7.1 | Load Building Permitting Data Into Production
7.2 | Test Building Permitting Production Configuration, Data
7.3 | Approve Building Permitting Go Live

## Project Schedule Ph 2 LU Perm
WBS No. |  | Month 6 | Month 7 | Month 8 | Month 9 | Month 10
Task/Phase
Berkeley, California
Land Use Permitting
2 | Planning Phase
2.1 | Update Comprehensive Project Plan
2.2 | Update Technical Infrastructure Design & Implementation Plan
3 | Land Use Permitting System Setup and Configuration Phase
3.1 | Conduct Land Use Permitting Weekly Walkthroughs
3.2 | Practice with New Land Use Permitting Functionality, Provide Feedback
3.3 | Update System Design Document
3.4 | Configure Land Use Permitting Installation, Forms, Notices, Letters, Reports
3.5 | Configure Land Use Permitting User Accounts and Rights
System Integration
3.6 | Update Integration Document
3.7 | Develop and Test Integration Programs
Land Use Permitting Data Conversion
3.8 | Develop Land Use Permitting Data Conversion Document
3.9 | Develop and Test Land Use Permitting Conversion Scripts
Land Use Permitting Data Conversion Acceptance
4 | Land Use Permitting System Readiness Phase
4.1 | Create Land Use Permitting User Acceptance Test Scripts and Plan
4.2 | Perform Land Use Permitting User Acceptance Testing
4.3 | Provide Feedback on Land Use Permitting Issues, Changes
4.4 | Update Citizenserve Land Use Permitting Configuration
4.5 | Conduct Pre-production Security Testing
5 | Land Use Permitting Training Phase
5.1 | Create Land Use Permitting Training Documents for City Users
5.2 | Provide Land Use Permitting Training for City Users
5.3 | Create Land Use Permitting Training Documents for City System Administrators
5.4 | Provide Land Use Permitting Training for City System Administrators
5.5 | Create Land Use Permitting System Documentation/Manuals
6 | Land Use Permitting Implementation Phase
6.1 | Develop Land Use Permitting Cutover Plan
6.2 | Configure Land Use Permitting Production Instance
6.3 | Configure Integration Points in Production
6.4 | Convert Land Use Permitting Legacy Data to Production
6.5 | Provide Supplemental Land Use Permitting Training
7 | Land Use Permitting Go-Live Phase
7.1 | Load Land Use Permitting Data Into Production
7.2 | Test Land Use Permitting Production Configuration, Data
7.3 | Approve Land Use Permitting Go Live

## Project Schedule Ph 3 ROW Perm
WBS No. |  | Month 11 | Month 12 | Month 13 | Month 14
Task/Phase
Berkeley, California
Right of Way Permitting
2 | Planning Phase
2.1 | Update Comprehensive Project Plan
2.2 | Update Technical Infrastructure Design & Implementation Plan
3 | Right of Way Permitting System Setup and Configuration Phase
3.1 | Conduct Right of Way Permitting Weekly Walkthroughs
3.2 | Practice with New Right of Way Permitting Functionality, Provide Feedback
3.3 | Update System Design Document
3.4 | Configure Right of Way Permitting Installation, Forms, Notices, Letters, Reports
3.5 | Configure Right of Way Permitting User Accounts and Rights
System Integration
3.6 | Update Integration Document
3.7 | Develop and Test Integration Programs
Right of Way Permitting Data Conversion
3.8 | Develop Right of Way Permitting Data Conversion Document
3.9 | Develop and Test Right of Way Permitting Conversion Scripts
Right of Way Permitting Data Conversion Acceptance
4 | Right of Way Permitting System Readiness Phase
4.1 | Create Right of Way Permitting User Acceptance Test Scripts and Plan
4.2 | Perform Right of Way Permitting User Acceptance Testing
4.3 | Provide Feedback on Right of Way Permitting Issues, Changes
4.4 | Update Citizenserve Right of Way Permitting Configuration
4.5 | Conduct Pre-production Security Testing
5 | Right of Way Permitting Training Phase
5.1 | Create Right of Way Permitting Training Documents for City Users
5.2 | Provide Right of Way Permitting Training for City Users
5.3 | Create Right of Way Permitting Training Documents for City System Administrators
5.4 | Provide Right of Way Permitting Training for City System Administrators
5.5 | Create Right of Way Permitting System Documentation/Manuals
6 | Right of Way Permitting Implementation Phase
6.1 | Develop Right of Way Permitting Cutover Plan
6.2 | Configure Right of Way Permitting Production Instance
6.3 | Configure Integration Points in Production
6.4 | Convert Right of Way Permitting Legacy Data to Production
6.5 | Provide Supplemental Right of Way Permitting Training
7 | Right of Way Permitting Go-Live Phase
7.1 | Load Right of Way Permitting Data Into Production
7.2 | Test Right of Way Permitting Production Configuration, Data
7.3 | Approve Right of Way Permitting Go Live

## Project Schedule Ph 4 Fire Perm
WBS No. |  | Month 15 | Month 16 | Month 17 | Month 18
Task/Phase
Berkeley, California
Fire Permitting
2 | Planning Phase
2.1 | Update Comprehensive Project Plan
2.2 | Update Technical Infrastructure Design & Implementation Plan
3 | Fire Permitting System Setup and Configuration Phase
3.1 | Conduct Fire Permitting Weekly Walkthroughs
3.2 | Practice with New Fire Permitting Functionality, Provide Feedback
3.3 | Update System Design Document
3.4 | Configure Fire Permitting Installation, Forms, Notices, Letters, Reports
3.5 | Configure Fire Permitting User Accounts and Rights
System Integration
3.6 | Update Integration Document
3.7 | Develop and Test Integration Programs
Fire Permitting Data Conversion
3.8 | Develop Fire Permitting Data Conversion Document
3.9 | Develop and Test Fire Permitting Conversion Scripts
Fire Permitting Data Conversion Acceptance
4 | Fire Permitting System Readiness Phase
4.1 | Create Fire Permitting User Acceptance Test Scripts and Plan
4.2 | Perform Fire Permitting User Acceptance Testing
4.3 | Provide Feedback on Fire Permitting Issues, Changes
4.4 | Update Citizenserve Fire Permitting Configuration
4.5 | Conduct Pre-production Security Testing
5 | Fire Permitting Training Phase
5.1 | Create Fire Permitting Training Documents for City Users
5.2 | Provide Fire Permitting Training for City Users
5.3 | Create Fire Permitting Training Documents for City System Administrators
5.4 | Provide Fire Permitting Training for City System Administrators
5.5 | Create Fire Permitting System Documentation/Manuals
6 | Fire Permitting Implementation Phase
6.1 | Develop Fire Permitting Cutover Plan
6.2 | Configure Fire Permitting Production Instance
6.3 | Configure Integration Points in Production
6.4 | Convert Fire Permitting Legacy Data to Production
6.5 | Provide Supplemental Fire Permitting Training
7 | Fire Permitting Go-Live Phase
7.1 | Load Fire Permitting Data Into Production
7.2 | Test Fire Permitting Production Configuration, Data
7.3 | Approve Fire Permitting Go Live